## _meta
EDD · ESPMO · GOVERNANCE RULES (round-trip schema)
Description | Regenerated FROM the live Profiler ESPMO_RULES block — questions, scoring, triggers, and the PAL calculation all derive from the same source, so the tool and this workbook cannot drift.
schema | RT-1.1
rulesVersion | 01.04
generatedFrom | Profiler ESPMO_RULES (32 questions, weighted value model, ESPMO_RULES.pal, ESPMO_RULES.tshirt)
zoneThreshold | 2.5
value.model | weighted 0/1/3/9 drivers, normalized to 100 (Σ weight×value / 135 × 100)
value.weightSum | 15
value.max | 135
pal.spec | SAM 4819.37 / SIMM 19
pal.palTier | 4
pal.config.EDD_COST_DELEGATION | None
pal.config.COST_KNOWN | False
govTier.palTier | 4
govTier.eddnextFloor | 3

## Questions
Intake questions — one row per question (options packed label¦value¦flag)
Q# | id | group | type | question | options (label¦value¦flag ; …) / help
— | name | Project Identity | text | Project name
|  |  |  | help ▸ | For the read-out header only. Doesn't affect scoring.
Q01 | method | Project Identity | select | What is the project delivery approach? | Agile¦agile ; Waterfall¦waterfall ; Hybrid¦hybrid ; Not yet determined¦tbd
|  |  |  | help ▸ | Determines delivery artifacts and scope / standards. Does not drive priority. An advisory recommendation is derived from your scope stability, delivery cadence, business-partner availability, team size, and team-availability answers to compare against this.
Q02 | scope | Project Identity | select | Once defined, how stable is the scope / set of requirements expected to be during delivery? | Stable — well-defined, few changes expected once set¦stable ; Mostly stable — some change expected¦mostly ; Volatile — frequent change expected or welcomed¦evolving ; Not sure¦ns
|  |  |  | help ▸ | Delivery-approach input (advisory only — does not affect value or complexity scores). DISTINCT from novelty: this is requirements VOLATILITY (will they hold or keep changing), not whether the work is new. Stable requirements favor predictive (Waterfall); changing requirements favor adaptive (Agile).
Q03 | delivery | Project Identity | select | How does the business want the solution delivered? | In stages — incremental releases over time¦stages ; Phased — a few planned releases¦phased ; All at once — single delivery at the end of the timeline¦end ; Not sure¦ns
|  |  |  | help ▸ | Delivery-approach input (advisory only — does not affect value or complexity scores). EDD SDLC “Delivery” criterion. Delivered in stages favors Agile; a single delivery at the end favors Waterfall.
Q04 | custavail | Project Identity | select | How available is the business partner / product owner during delivery? | Available throughout — ongoing collaboration¦through ; Periodic — at key checkpoints¦periodic ; At requirements and milestones only¦miles ; Not sure¦ns
|  |  |  | help ▸ | Delivery-approach input (advisory only — does not affect value or complexity scores). Availability throughout favors Agile; engagement at milestones only favors Waterfall.
Q05 | teamavail | Project Identity | select | Is the delivery team dedicated and available to this project? | Dedicated — committed and available to this project¦ded ; Mostly available — some competing work¦mostly ; Shared / part-time — pulled across other work¦shared ; Not sure¦ns
|  |  |  | help ▸ | Delivery-approach input (advisory only — does not affect value or complexity scores). EDD SDLC “Resources” criterion (with team size). A dedicated, available team favors Agile; a team shared / part-time across other work favors hand-off, plan-driven Waterfall.
Q06 | phase | Project Identity | select | What is the current project phase? | Concept¦Concept ; Initiate¦Initiate ; Plan¦Plan ; Execute¦Execute ; Close¦Close
|  |  |  | help ▸ | Determines which artifacts are expected now vs. later.
Q07 | benefit | Value / Priority Drivers | select | What is the expected strategic or operational value if this project succeeds? | Incremental¦inc ; Moderate¦mod ; High¦high ; Transformational¦trans
|  |  |  | help ▸ | Drives the Value Score.
Q08 | mandate | Value / Priority Drivers | select | Is there a hard external driver — required deadline, statutory/regulatory requirement, policy/compliance requirement, audit finding, funding deadline, executive mandate, time-related contract restriction or expiration, end-of-life / unsupported system deadline, or other non-discretionary driver? | No¦n ; Yes¦y ; Not sure¦m
|  |  |  | help ▸ | Time driver (weight 4). Any hard, non-discretionary deadline — including an end-of-life/unsupported system or a contract time restriction — counts as Yes.
Q09 | risk | Value / Priority Drivers | select | Are the project's risks identified and under control? | All under control — risks identified, owned, and actively mitigated¦all ; Mostly — key risks managed, some gaps remain¦most ; Minimal — few risks identified or mitigated¦few ; None — risks unknown or unmanaged¦none ; Not sure¦ns
|  |  |  | help ▸ | Risk Management (weight 3). Higher = better risk posture — risks identified, owned, and actively mitigated. Anchor on what's documented (risk log / mitigation plan), not optimism.
Q10 | impact | Value / Priority Drivers | select | Who is expected to be impacted by the project outcome? | Internal project team only¦team ; One unit or program area¦div ; Multiple units or divisions¦multi ; External customers, claimants, employers, or public users¦public¦public
|  |  |  | help ▸ | Operational / customer impact and priority value.
Q11 | pmexp | Value / Priority Drivers | select | How experienced is the delivery team with this type of work? | Very experienced — delivered multiple comparable projects; key roles held by people who've done it before¦ve ; Somewhat experienced — adjacent or partial experience; some key roles experienced, some new¦sw ; New to this type of work — first time; learning on the job, or key roles unfilled¦ne ; Not sure / not yet assessed¦ns
|  |  |  | help ▸ | People half of Resource Availability (People + Funding, each worth half). Anchor on the observable test: HAS THIS TEAM DELIVERED THIS TYPE OF WORK BEFORE? Rate the collective team, not any one person. Also cross-checks SIMM team experience.
Q12 | funding | Value / Priority Drivers | select | Is funding secured for this work? | Secured / fully funded¦sec ; Partially funded or in the budget cycle¦part ; Identified but not yet secured¦id ; Not funded / no funding identified¦none ; Not sure¦ns
|  |  |  | help ▸ | Funding half of Resource Availability (People + Funding, each worth half). An experienced team with no funding earns only the people half of the score.
Q13 | newcap | Size & Delivery Footprint | select | Will this project deliver a new or changed service, system, process, or capability? | No¦n ; Not sure¦m ; Yes¦y¦production
|  |  |  | help ▸ | Service-delivery value and artifact needs.
Q14 | spend | Size & Delivery Footprint | select | What is the estimated project cost or funding range? | Under $250K¦s ; $250K–$1M¦m ; Over $1M¦l ; Unknown¦u
|  |  |  | help ▸ | SIMM financial risk and delivery footprint.
Q15 | loe | Size & Delivery Footprint | select | What is the estimated level of effort (T-shirt size)? | Small — under 500 hrs¦s ; Medium — 500–10,000 hrs¦m ; Large — over 10,000 hrs¦l ; Not yet sized¦u
|  |  |  | help ▸ | TRT sizing by estimated effort hours — a sizing/tracking signal, separate from cost, complexity, and value. Small < 500 hrs · Medium 500–10,000 hrs · Large > 10,000 hrs.
Q16 | eddnext | Size & Delivery Footprint | select | Is this an EDD Next project? | No¦n ; Yes¦y¦eddnext
|  |  |  | help ▸ | EDD Next program scope. Governance-tier driver — an EDD Next project is at least Tier 3 (and Tier 4 if PAL also applies). Does not change complexity or value.
Q17 | coord | Size & Delivery Footprint | select | How many teams, units, or divisions need to coordinate for delivery? | One team (1)¦1 ; A few teams or units (2–4)¦2 ; Several teams or divisions (5–9)¦3 ; Many groups across organizational lines (10+)¦4
|  |  |  | help ▸ | Business complexity: interaction, decision-making, authority.
Q18 | vendor | Size & Delivery Footprint | select | Are vendors or contractors responsible for delivering part or all of the project? | No, internal delivery only¦n ; One vendor or contractor (1)¦1¦vendor ; A few vendors or contractors (2–4)¦few¦vendor ; Several vendors or contractors (5–9)¦sev¦vendor ; Many vendors or contractors (10+)¦mlt¦vendor ; Not sure¦ns
|  |  |  | help ▸ | Team / vendor complexity and artifact expectations.
Q19 | pal_budget | PAL Determination | select | Does the project require a budget action — a BCP (Budget Change Proposal) or Budget Revision? | No¦n ; Yes¦y ; Not sure¦ns
|  |  |  | help ▸ | PAL trigger (SAM 4819.37). Any Yes anticipates a PAL / CDT-reportable project. Advisory — the tool flags anticipated PAL status; confirm at PAL Stage 1 (SIMM 19A.2). Does not change complexity or value.
Q20 | pal_legis | PAL Determination | select | Is the project required by a legislative mandate, or subject to special legislative review? | No¦n ; Yes¦y ; Not sure¦ns
|  |  |  | help ▸ | PAL trigger (SAM 4819.37). Advisory — the tool flags anticipated PAL status; confirm at PAL Stage 1 (SIMM 19A.2). Does not change complexity or value.
Q21 | pal_govbudget | PAL Determination | select | Does project initiation depend on Governor’s Budget decisions? | No¦n ; Yes¦y ; Not sure¦ns
|  |  |  | help ▸ | PAL trigger (SAM 4819.37). Advisory — the tool flags anticipated PAL status; confirm at PAL Stage 1 (SIMM 19A.2). Does not change complexity or value.
Q22 | pal_crit | PAL Determination | select | Has CDT/AIO determined the project’s criticality or risk warrants CDT oversight? | No¦n ; Yes¦y ; Not sure¦ns
|  |  |  | help ▸ | PAL trigger (SAM 4819.37). Advisory — the tool flags anticipated PAL status; confirm at PAL Stage 1 (SIMM 19A.2). Does not change complexity or value.
Q23 | data | Technical / Business Complexity | select | Does the project involve sensitive, personal, confidential, regulated data, FTI, or other protected data? | No¦n ; Not sure¦m ; Yes¦y¦pii
|  |  |  | help ▸ | Security / PII floor; artifact and complexity trigger.
Q24 | deps | Technical / Business Complexity | select | Does the project depend on other systems, integrations, interfaces, or shared data? | Standalone or minimal dependencies¦n ; A few dependencies (2–4)¦f ; Several dependencies (5–9)¦sev ; Many or critical dependencies (10+)¦m¦deps ; Not sure¦ns
|  |  |  | help ▸ | Technical complexity and integration artifacts.
Q25 | migrate | Technical / Business Complexity | select | Will existing data be migrated, converted, cleansed, or loaded at scale? | No¦n ; Yes¦y¦migration ; Not sure¦ns
|  |  |  | help ▸ | Data conversion / migration trigger.
Q26 | novelTech | Technical / Business Complexity | select | How familiar is the technology to IT? | Previously implemented¦n ; Some new components¦s ; Largely new or unproven¦y¦archnew ; Not sure¦ns
|  |  |  | help ▸ | Technical complexity — feeds Delivery, Architecture, Hardware, Networks, Software, Team.
Q27 | novelBiz | Technical / Business Complexity | select | How familiar is the business process or operational model to the business area? | Previously implemented¦n ; Some new components¦s ; Largely new or unproven¦y ; Not sure¦ns
|  |  |  | help ▸ | Business complexity — feeds Rules, Requirements, Objectives, Process Impact, Systems.
Q28 | sec | Technical / Business Complexity | select | Will the project require new access controls, authentication changes, or a formal security review? | No¦n ; Maybe¦mb¦security ; Yes¦y¦security ; Not sure¦ns
|  |  |  | help ▸ | Security artifact trigger and technical complexity.
Q29 | cloud | Technical / Business Complexity | select | Does the project involve cloud, hosting, infrastructure, or environment changes? | No¦n ; Yes¦y¦cloud ; Not sure¦ns
|  |  |  | help ▸ | Artifact trigger only — does not auto-increase complexity unless other technical answers justify it.
Q30 | testing | Sustainment Planning | select | How will testing be performed for this project? | In-house QA / project team¦inhouse ; Vendor-led testing¦vendor_test ; Hybrid (vendor + in-house)¦hybrid_test ; Not yet defined¦tbd_test ; Not applicable (no software change)¦na
|  |  |  | help ▸ | EA Readiness alignment — Testing. Drives Test Strategy artifact.
Q31 | support | Sustainment Planning | select | What is the planned post-deployment support and M&O strategy? | Internal IT operations support¦internal ; Vendor-supported¦vendor_sup ; Hybrid internal/vendor support¦hybrid_sup ; Not yet defined / not applicable¦na
|  |  |  | help ▸ | EA Readiness alignment — Support and M&O. Drives Operations, Support & M&O Plan artifact.

## Value
Value scoring — weighted 0/1/3/9 prioritization drivers (normalized to 100)
Total value = round( Σ (weight × selected 0/1/3/9 value) / 135 × 100 ). Σ weights = 15.
criterion | weight | source question | % share of value | value map (answer → 0/1/3/9)
Resource Availability — People | 0.5 | pmexp | 3.3 | ve→9, sw→3, ne→1, ns→3
Resource Availability — Funding | 0.5 | funding | 3.3 | sec→9, part→3, id→1, none→0, ns→3
Customer / Stakeholder Value | 2 | impact | 13.3 | team→1, div→3, multi→9, public→9
Risk Management | 3 | risk | 20 | all→9, most→3, few→1, none→0, ns→3
Time / Mandate | 4 | mandate | 26.7 | n→0, m→3, y→9
Strategic Alignment | 5 | benefit | 33.3 | inc→1, mod→3, high→9, trans→9

## Value_Score_Responses
Value scoring — per-response points (0/1/3/9) and weighted contribution
criterion | weight | source question | answer value | 0/1/3/9 | weighted contribution to 100
Resource Availability — People | 0.5 | pmexp | ve | 9 | 3.33
Resource Availability — People | 0.5 | pmexp | sw | 3 | 1.11
Resource Availability — People | 0.5 | pmexp | ne | 1 | 0.37
Resource Availability — People | 0.5 | pmexp | ns | 3 | 1.11
Resource Availability — Funding | 0.5 | funding | sec | 9 | 3.33
Resource Availability — Funding | 0.5 | funding | part | 3 | 1.11
Resource Availability — Funding | 0.5 | funding | id | 1 | 0.37
Resource Availability — Funding | 0.5 | funding | none | 0 | 0
Resource Availability — Funding | 0.5 | funding | ns | 3 | 1.11
Customer / Stakeholder Value | 2 | impact | team | 1 | 1.48
Customer / Stakeholder Value | 2 | impact | div | 3 | 4.44
Customer / Stakeholder Value | 2 | impact | multi | 9 | 13.33
Customer / Stakeholder Value | 2 | impact | public | 9 | 13.33
Risk Management | 3 | risk | all | 9 | 20
Risk Management | 3 | risk | most | 3 | 6.67
Risk Management | 3 | risk | few | 1 | 2.22
Risk Management | 3 | risk | none | 0 | 0
Risk Management | 3 | risk | ns | 3 | 6.67
Time / Mandate | 4 | mandate | n | 0 | 0
Time / Mandate | 4 | mandate | m | 3 | 8.89
Time / Mandate | 4 | mandate | y | 9 | 26.67
Strategic Alignment | 5 | benefit | inc | 1 | 3.7
Strategic Alignment | 5 | benefit | mod | 3 | 11.11
Strategic Alignment | 5 | benefit | high | 9 | 33.33
Strategic Alignment | 5 | benefit | trans | 9 | 33.33

## RatingMaps
Rating maps — shared 0–4 answer scales feeding SIMM complexity
map | answer | score
NOVELTY_HIGH | n | 1
NOVELTY_HIGH | s | 2.5
NOVELTY_HIGH | y | 4
NOVELTY_HIGH | ns | 2.5
NOVELTY_MODERATE | n | 1
NOVELTY_MODERATE | s | 2.5
NOVELTY_MODERATE | y | 3.5
NOVELTY_MODERATE | ns | 2.5
COORD | 1 | 0.5
COORD | 2 | 1.5
COORD | 3 | 2.5
COORD | 4 | 4
IMPACT | team | 0.5
IMPACT | div | 1.5
IMPACT | multi | 2.5
IMPACT | public | 4
OPS | team | 0.5
OPS | div | 1.5
OPS | multi | 2.5
OPS | public | 3.5
SPEND | s | 1
SPEND | m | 2.5
SPEND | l | 4
SPEND | u | 2.5
VEND | 1 | 2
VEND | n | 1
VEND | few | 2.5
VEND | sev | 3
VEND | mlt | 3.5
VEND | ns | 2
DEPS | n | 0.5
DEPS | f | 2
DEPS | sev | 3
DEPS | m | 4
DEPS | ns | 2
PMX | ve | 1
PMX | sw | 2.5
PMX | ne | 4
PMX | ns | 2.5
METH | agile | 1.5
METH | waterfall | 1
METH | hybrid | 1.5
METH | tbd | 3.5

## SIMM_Biz
SIMM business complexity axis
factor | source question | score map
Business Rules | novelBiz | @NOVELTY_HIGH
Current Business Systems | novelBiz | @NOVELTY_HIGH
Decision-Making Process | coord | @COORD
Financial Risk to State | spend | @SPEND
Geography | impact | @IMPACT
High-Level Requirements | novelBiz | @NOVELTY_HIGH
Interaction w/ Other Depts | coord | @COORD
Impact to Business Process | novelBiz | @NOVELTY_HIGH
Issues | mandate | {"n": 1, "y": 3.5, "m": 2}
Level of Authority | coord | @COORD
Objectives | novelBiz | @NOVELTY_MODERATE
Policies | mandate | {"n": 1, "y": 3, "m": 2}
Politics | impact | @IMPACT
Target Users | impact | @IMPACT
Team Experience | pmexp | @PMX
Team | vendor | @VEND
Time Scale | mandate | {"n": 1.5, "y": 3.5, "m": 2.5}
Visibility | impact | @IMPACT

## SIMM_Tech
SIMM technical complexity axis
factor | source question | score map
Communications | impact | @IMPACT
Delivery Mechanism | novelTech | @NOVELTY_HIGH
Geography | impact | @IMPACT
Hardware | novelTech | @NOVELTY_MODERATE
Level of Integration | deps | @DEPS
Networks (L/W) | novelTech | @NOVELTY_MODERATE
New Technology Architecture | novelTech | @NOVELTY_HIGH
Operations | impact | @OPS
Team Technical Experience | pmexp | @PMX
Scope Management Process | method | @METH
Security | (max) | MAX of data:{"n": 0.5, "m": 2, "y": 4}; sec:{"n": 0.5, "mb": 2.5, "y": 4, "ns": 2.5}
Software | novelTech | @NOVELTY_HIGH
Standards & Methods | method | @METH
Team | novelTech | @NOVELTY_MODERATE
Tolerance to Fault | (max) | MAX of data:{"n": 1, "m": 2, "y": 3.5}; impact:@IMPACT
Transaction Volume | impact | @IMPACT

## Triggers
Triggers → documents (flag origin pulls each document in)
origin (flag) | document | category | phase | note
baseline | EAO Project Engagement Plan | Initiation & Baseline | Initiate
baseline | Stakeholder Register | Initiation & Baseline | Initiate
baseline | Engagement Matrix | Initiation & Baseline | Initiate
baseline | RACI | Initiation & Baseline | Initiate
baseline | RAID / CRAID Log | Initiation & Baseline | Ongoing
baseline | Project Schedule | Planning | Plan
baseline | Implementation Plan | Release & Production | Execute
baseline | Status Reporting | Closeout & Governance | Ongoing
baseline | Closeout Report | Closeout & Governance | Close
baseline | Lessons Learned | Closeout & Governance | Close
baseline | Delegated Approvals | Closeout & Governance | Ongoing
tier3 | Project Governance Plan | Closeout & Governance | Plan
tier3 | Governance / Steering-Committee Reporting | Closeout & Governance | Ongoing
tier3 | Risk Management Plan | Planning | Plan
tier3 | Quality Management Plan | Planning | Plan
tier3 | Communications Management Plan | Planning | Plan
tier3 | Change & Schedule Management Plan | Planning | Plan
tier3 | Scope Management Plan | Planning | Plan
tier3 | Requirements Management Plan | Planning | Plan
tier3 | Organization Management Plan | Planning | Plan
tier3 | Procurement Management Plan | Planning | Plan
tier3 | Cost Management Plan | Planning | Plan
tier3 | Post-Implementation Review | Closeout & Governance | Close
method:predictive | Requirements Documentation | Planning | Plan
method:predictive | Test Plan & Test Cases | Planning | Plan
method:predictive | Training Plan | Planning | Plan
method:predictive | Transition Plan | Planning | Plan
method:predictive | Requirements Traceability Matrix | Planning | Plan
method:agile | Product Vision | Planning | Plan
method:agile | Product Backlog | Planning | Plan
method:agile | Roadmap / Sprint Planning | Planning | Plan
flag:production | Rollback Plan | Release & Production | Execute | new service
flag:production | RFC / RRB | Release & Production | Execute | new service
flag:production | RRR Checklist | Release & Production | Execute | new service
flag:production | Hypercare / Production Readiness | Release & Production | Execute | new service
flag:pii | Privacy Impact Assessment (PIA) | Security & Risk | Initiate | sensitive data
flag:pii | Business Impact Analysis (BIA) | Security & Risk | Execute | sensitive data
flag:pii | System Security Plan (SSP) — Initial (Sections 1 & 2) | Security & Risk | Initiate | sensitive data
flag:pii | Risk Assessment | Security & Risk | Execute | sensitive data
flag:security | C&A Package | Security & Risk | Execute | security review
flag:security | ISRP | Security & Risk | Execute | security review
flag:security | SIEM / Logging Kickoff | Security & Risk | Execute | security review
flag:security | Vulnerability Scan & Pen Test | Security & Risk | Execute | security review
flag:cloud | Cloud Architecture Diagram | Planning | Plan | cloud / infra
flag:cloud | Cloud Documentation | Security & Risk | Execute | cloud / infra
flag:cloud | Cloud Review | Security & Risk | Execute | cloud / infra
flag:cloud | TARC | Security & Risk | Execute | cloud / infra
flag:vendor | Vendor SOW & Contract Oversight | Planning | Plan | vendor-delivered
flag:migration | Data Migration / Conversion Plan | Planning | Plan | data migration
flag:pal | PAL Stage 1-4 Gate Package (CDT / SIMM 19) | Initiation & Baseline | Initiate | PAL applies
flag:__state_testing | Test Strategy | Quality & Sustainment | Plan | testing
flag:__state_support | Operations, Support & M&O Plan | Quality & Sustainment | Execute | support / M&O
flag:archnew | Solution Architecture Document (SAD) | Planning | Plan | new/unproven technology architecture

## TierQuestionIds
Tier-driving question ids (high answers can push the complexity tier)
question id
data
impact
spend
coord
vendor
deps
novelTech
novelBiz
mandate
sec
method
pmexp

## PAL_Determination
PAL Determination — SAM 4819.37 / SIMM 19 (how the Profiler calculates PAL)
This is the exact rule the Profiler runs (ESPMO_RULES.pal). PAL rolls up to a separate governance tier (Tier 4) above Full.
Decision rule
PAL | Any trigger = Yes → PAL (Non-Delegated, CDT-reportable). | → status: | PAL — Non-Delegated (Reportable to CDT)
INDETERMINATE | No trigger Yes but a trigger is Unknown → Indeterminate (likely Regular; confirm cost against EDD delegation tier). | → status: | INDETERMINATE — likely Regular; confirm cost against EDD delegation tier
REGULAR | All triggers = No → Regular (Delegated, not CDT-reportable). | → status: | Regular Project — Delegated (not CDT-reportable)
Cost trigger configuration (SIMM 15A / delegation agreement)
EDD_COST_DELEGATION | None | COST_KNOWN | False | While COST_KNOWN is false the cost trigger returns UNKNOWN → INDETERMINATE when triggers 2–5 are all No.
Triggers (any Yes ⇒ PAL)
# | trigger key | source question id | Yes value | label / meaning
1 | cost_exceeds_delegation | (cost vs. delegation tier — config) | — | Cost exceeds EDD delegation tier
2 | budget_action_required | pal_budget | y | Budget action (BCP / Budget Revision)
3 | legislative_mandate_or_review | pal_legis | y | Legislative mandate or special review
4 | governors_budget_dependency | pal_govbudget | y | Depends on Governor’s Budget decisions
5 | criticality_risk_determination | pal_crit | y | CDT/AIO criticality / risk determination
Disclaimer | Anticipated / preliminary — confirm at PAL Stage 1 (SIMM 19A.2).
Anti-splitting (SAM 4819.37) | Do not split scope or cost to stay under the delegation line.

## Tshirt_Templates
CA-PMF T-shirt template matrix — Required (R) / Recommended (O) per profile
Profile column chosen PAL → delivery approach → Waterfall T-shirt size. R = Required, O = Recommended/optional, blank = not needed.
template | file | phase | owner | PAL | Hybrid-Agile | WF-Large | WF-Medium | WF-Small | SharePoint path | note
Concept Development and Readiness Assessment | Concept_Development_and_Readiness_Assessment_Template_with_Instructions.docx | A. Concept |  | R | R | R |  |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF CONCEPT_Templates_w_Instructions | Replaced by EDD Work Intake process
Concept Process Phase Checklist | Concept_Process_Phase_Checklist_Template_with_Instructions.docx | A. Concept |  | O |  | R |  |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF CONCEPT_Templates_w_Instructions
Initiating Process Phase Checklist | Initiating_Process_Phase_Checklist_Template_with_Instructions.docx | B. Initiation |  | O |  |  |  |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF INITIATING_Templates_w_Instructions
Project Charter Mini | Project_Charter_Mini_Template_with_Instructions.docx | B. Initiation |  |  |  |  | R | R | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF INITIATING_Templates_w_Instructions
Project Charter | Project_Charter_Template_with_Instructions.docx | B. Initiation |  | R |  | R |  |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF INITIATING_Templates_w_Instructions | Required for PAL Projects
Hybrid-Agile Project Charter | (to build) | B. Initiation |  |  | R |  |  |  |  | New template to be created for Hybrid-Agile only
Project Document Approval | Project_Document_Approval_Template_with_Instructions.docx | B. Initiation |  | O | O | O |  |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF INITIATING_Templates_w_Instructions | Only needed for a project that needs formal document or deliverable sign-offs
Project Priorities | Project_Priorities_Template_with_Instructions.docx | B. Initiation |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF INITIATING_Templates_w_Instructions | Optional template
RACI Matrix Mini | RACI_Matrix_Mini_Template_with_Instructions.xlsx | B. Initiation |  |  |  | R | R |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF INITIATING_Templates_w_Instructions | CA-PMF template should be for PAL projects only (USE NEW VERSION RACI)
RACI Matrix | RACI_Matrix_Template_with_Instructions.xlsx | B. Initiation |  | R | R | R | R |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF INITIATING_Templates_w_Instructions | CA-PMF template should be for PAL projects only (USE NEW VERSION OF RACI)
Stakeholder Register | Stakeholder_Register_Template_with_Instructions.docx | B. Initiation |  | R | R | R | R | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF INITIATING_Templates_w_Instructions | Recommended for all sizes of projects but only required for large & medium
Hybrid-Agile Product Roadmap | (to build) | C. Planning |  |  | R |  |  |  |  | New template to be created for Hybrid-Agile only
Change Control Management Plan | Change_Control_Management_Plan_Template_with_Instructions.docx | C. Planning | PMO | R | O | R | O |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Required for large, recommended for medium
Change Request Form | Change_Request_Form_Template_with_Instructions.docx | C. Planning | PM | R | O | R | O |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Required for large, recommended for medium
Change Request Log | Change_Request_Log_Template_with_Instructions.xlsx | C. Planning |  | O | O | R | O |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Required for large and medium
Communications Management Plan | Communications_Management_Plan_Template_with_Instructions.docx | C. Planning |  | R | O | R | O |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Required for large, recommended for medium
Contract Management Plan | Contract_Management_Plan_Template_with_Instructions.docx | C. Planning |  | R | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Optional for any size project except PAL
Corrective Action Plan | Corrective_Action_Plan_Template_with_Instructions.docx | C. Planning |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Optional for any size project
Cost Management Plan | Cost_Management_Plan_Template_with_Instructions.docx | C. Planning |  | R | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Optional for any size project except PAL
Governance Management Plan | Governance_Management_Plan_Template_with_Instructions.docx | C. Planning |  | R | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Optional for any size project except PAL
Implementation Management Plan | Implementation_Management_Plan_Template_with_Instructions.docx | C. Planning |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Optional for any size project
Issue Log | Issue_Log_Template_with_Instructions.xlsx | C. Planning |  | R | O | R | R |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions
Issue Management Plan | Issue_Management_Plan_Template_with_Instructions.docx | C. Planning |  | R | O | R | R |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions
Maintenance and Operations Transition Management Plan | Maintenance_and_Operations_Transition_Management_Plan_Template_with_Instructions.docx | C. Planning |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Optional for any size project
Meeting Agenda and Minutes | Meeting_Agenda_and_Minutes_Template_with_Instructions.docx | C. Planning |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Optional for any size project
Planning Process Phase Checklist | Planning_Process_Phase_Checklist_Template_with_Instructions.docx | C. Planning |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Optional for any size project
Procurement Management Plan | Procurement_Management_Plan_Template_with_Instructions.docx | C. Planning |  | R | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Optional for any size project
Agile-Hybrid Project Management Plan | (to build) | C. Planning |  |  | R |  |  |  |  | New template to be created for Hybrid-Agile only
Project Management Plan PMP Mini | Project_Management_Plan_PMP_Mini_Template_with_Instructions.docx | C. Planning |  |  |  |  | R |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions
Project Management Plan PMP | Project_Management_Plan_PMP_Template_with_Instructions.docx | C. Planning |  |  |  | R |  |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions
Project Org Chart | Project_Org_Chart_Template_with_Instructions.docx | C. Planning |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Optional for any size project
Quality Management Plan | Quality_Management_Plan_Template_with_Instructions.docx | C. Planning |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Optional for any size project
Requirements Management Plan | Requirements_Management_Plan_Template_with_Instructions.docx | C. Planning |  | R |  | R |  |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Recommended for all sizes of projects but only required for Waterfall large
Requirements Traceability Matrix | Requirements_Traceability_Matrix_Template_with_Instructions.xlsx | C. Planning |  | R |  | R |  |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Recommended for all sizes of projects but only required for Waterfall large
Resource Management Plan | Resource_Management_Plan_Template_with_Instructions.docx | C. Planning |  | R | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Optional for any size project except PAL
Risk Management Plan | Risk_Management_Plan_Template_with_Instructions.docx | C. Planning |  | R | R | R | R |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions
Risk Register | Risk_Register_Template_with_Instructions.xlsx | C. Planning |  | R | R | R | R |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions
Schedule Management Plan | Schedule_Management_Plan_Template_with_Instructions.docx | C. Planning |  | R |  | R | R | R | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Required for large T-Shirt size but recommended for all sizes
Scope Management Plan | Scope_Management_Plan_Template_with_Instructions.docx | C. Planning |  | R |  | R |  |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions
Scope Management | Scope_Management_Template_with_Instructions.docx | C. Planning |  | O |  | R |  |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions
Skills Assessment | Skills_Assessment_Template_with_Instructions.docx | C. Planning |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Optional for any size project
Stakeholder Management Plan | Stakeholder_Management_Plan_Template_with_Instructions.docx | C. Planning |  | R | R | R | R | R | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Required for large & medium but recommended for all sizes
WBS | WBS_Template_with_Instructions.docx | C. Planning |  | O |  | R |  |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF PLANNING_Templates_w_Instructions | Recommended for Waterfall large T-shirt
Product Backlog for Hybrid-Agile projects | (to build) | C. Planning |  |  | R |  |  |  |  | New template to be created for Hybrid-Agile only
Deliverable Expectation Document | Deliverable_Expectation_Document_Template_with_Instructions.docx | D. Execution |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF EXECUTING_Templates_w_Instructions | Optional for any size project
Executing Process Phase Checklist | Executing_Process_Phase_Checklist_Template_with_Instructions.docx | D. Execution |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF EXECUTING_Templates_w_Instructions | Optional for any size project
Formal Product Acceptance | Formal_Product_Acceptance_Template_with_Instructions.docx | D. Execution |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF EXECUTING_Templates_w_Instructions | Optional for any size project
Operational Readiness Assessment ORA | Operational_Readiness_Assessment_ORA_Template_with_Instructions.docx | D. Execution |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF EXECUTING_Templates_w_Instructions | Optional for any size project
Process Improvement Plan | Process_Improvement_Plan_Template_with_Instructions.docx | D. Execution |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF EXECUTING_Templates_w_Instructions | Optional for any size project
Sponsorship Commitment Survey | Sponsorship_Commitment_Survey_Template_with_Instructions.docx | D. Execution |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF EXECUTING_Templates_w_Instructions | Optional for any size project
Team Effectiveness Survey | Team_Effectiveness_Survey_Template_with_Instructions.docx | D. Execution |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF EXECUTING_Templates_w_Instructions | Optional for any size project
Work Authorization | Work_Authorization_Template_with_Instructions.docx | D. Execution |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF EXECUTING_Templates_w_Instructions | Optional for any size project
Closing Process Phase Checklist | Closing_Process_Phase_Checklist_Template_with_Instructions.docx | E. Close |  | O | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF CLOSING_Templates_w_Instructions | Optional for any size project
Lessons Learned | Lessons_Learned_Template_with_Instructions.docx | E. Close |  | R |  |  |  |  | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF CLOSING_Templates_w_Instructions | We have a new template covering this category, now managed by Chizoba
Retrospective (Lessons Learned) | (to build) | E. Close |  | O | R | R | R | R
Project Closeout Report | Project_Closeout_Report_Template_with_Instructions.docx | E. Close |  | R | O | O | O | O | sites/ITB-TGD-PRO/Templates/Project Templates/CA-PMF CLOSING_Templates_w_Instructions | Optional for any size project