## Read Me
⚠ THIS IS A TEMPLATE — NOT A LIVE PROJECT SCHEDULE ⚠
Anticipation: the enterprise PPM tool (once selected) will produce the authoritative, project-specific schedule. This workbook is a reusable starter scaffold supporting both Waterfall and Agile delivery, combining EDD PM RACI (Most recent version), the Secure-by-Design guide, and PMI/PMBOK-standard PM deliverables.
KEY IN THIS VERSION — BASELINE PHASE COLUMN
Every deliverable has TWO lifecycle anchors: where active work STARTS, and where the final version is BASELINED. The new 'Baseline Phase' column (col F) shows where each deliverable is approved/finalized.
• 23 deliverables: Baseline Phase = Start Phase (same-phase, no span).
• 20 deliverables: Baseline Phase is later than Start Phase — highlighted with peach background and → arrow.
Example: Requirements Traceability Matrix (RTM) starts active work in Plan but isn't baselined until end of Test.
WHAT'S IN THIS WORKBOOK
• Schedule — PM-expected deliverables with Source / Methodology / Baseline Phase classifications and Profiler Required? filtering.
• Engagement Matrix — The Profiler provides the suggested matrix; the schedule keeps a Review and Revise Engagement Matrix task for PM follow-through.
• Phase Summary — Auto-rollup by CA-PMF phase, baseline phase, methodology, and source.
• Contacts — Seven EDD support groups referenced in the Secure-by-Design guide.
METHODOLOGY COVERAGE — WORKS FOR BOTH WATERFALL AND AGILE
Each deliverable is tagged with one of three values in the Methodology column:
• Agile (orange badge) — Scrum/Agile-specific artifacts that don't apply to Waterfall.
• Waterfall (indigo badge) — Formal upfront artifacts that Agile substitutes with iterative equivalents.
• Both (green badge) — Method-agnostic deliverables that apply regardless of delivery approach.
For a Waterfall project: include all 'Both' + 'Waterfall' rows; mark 'Agile' rows as N/A.
For an Agile project: include all 'Both' + 'Agile' rows; mark 'Waterfall' rows as N/A.
For Hybrid: keep all rows.
METHODOLOGY-SPECIFIC DELIVERABLES
Agile-only (2):
• PLN-03 Product Vision & Initial Product Backlog & Roadmap/Sprint Planning
• EXE-18 Generate/Update Product Backlog, Sprint Backlog, Product Increment & Sprint Retrospective
Waterfall-only (2):
• PLN-04 Requirements Documentation — comprehensive upfront documentation. Agile substitutes the Product Backlog (PLN-03).
• PLN-06 Test Plan & Test Cases — formal upfront test strategy. Agile uses sprint-level test cases.
Everything else (39): applies to both methodologies — Charter, Governance, RACI, CRAID, PMP, Implementation Plan, Rollback Plan, security deliverables, UAT, Training, etc.
PMI CONSOLIDATIONS APPLIED IN THIS VERSION
Four redundant deliverables removed because PMBOK treats them as duplicates:
• 'Create a Project Plan' (was INI) — duplicates the consolidated PMP (PLN-01).
• 'PIA (Initiate kick-off)' — duplicates EXE PIA Detailed.
• 'SSP (Initiate kick-off)' — duplicates EXE SSP §1-2.
• 'Develop Go-Live Readiness Plan' — overlaps with Implementation Plan + Transition Plan.
One merge applied:
• 'Define the Solution Architecture' (RACI) merged into 'Solution Architecture Document (SAD)' at EXE-07. One architecture deliverable, not two.
Three PMBOK-aligned deliverables relocated to Plan phase (work originates there, not in Execute):
• PLN-04 Requirements Documentation — PMBOK 'Collect Requirements' is a Planning process. Baseline established in Plan; refinements continue through Test via RTM.
• PLN-05 Requirements Traceability Matrix (RTM) — initialized in Plan alongside requirements; maintained continuously through System Testing and UAT.
• PLN-10 Training Plan & Materials — Training strategy and approach planned in Plan; materials development continues into Execute leading up to go-live.
Eight subsidiary plans consolidated into PLN-01 (PMP) per PMBOK (kept from prior version).
DELIVERABLE ID SCHEME
Deliverables use phase-prefix codes, not numeric WBS: CON-01, INI-01..08, PLN-01..11, EXE-01..19, CLS-01..04.
Column header 'Deliverable ID' signals each row is a PM-expected deliverable.
SCHEDULING MODEL — PHASE-PARALLEL
Tasks within a phase (or Execute sub-phase) run in PARALLEL. Phases sequence.
Concept → Initiate → Plan → Execute → Close.
Within Execute: Sec Analysis → Design → Test → Implement. 'Ongoing' runs throughout.
Note: Execute → 'Sec Analysis' covers security categorization deliverables (BIA, PIA Detailed, RA, SSP §1-2) per the Secure-by-Design guide. PMBOK 'Requirements Documentation' lives in Plan (PLN-04), not Execute — work originates in Planning per PMBOK.
Each block 'completes' when the longest task in it finishes (the gate).
HOW TO USE
1. Open the Schedule sheet.
2. Edit the four project info fields at the top (Project Name, PM, Project Start Date, Last Updated).
3. Set your project methodology — use the Methodology column to mark Agile-only or Waterfall-only rows as N/A if they don't apply.
4. Adjust Duration per your project. Update Status and % Complete as work progresses.
5. Dates auto-recalculate via WORKDAY().
CONVENTIONS
• Blue, bold text = user input. Black = formula.
• Source color codes: teal = RACI, gold = Secure-by-Design, violet = PMI/PMBOK.
• Methodology color codes: orange = Agile, indigo = Waterfall, green = Both.
• Duration in business days; weekends auto-skip; holidays not modeled (PPM tool handles).
SOURCES & ALIGNMENT
• EDD PM Engagement Matrix — source model used by the Profiler; schedule retains review/revise accountability without duplicating the matrix tab.
• EDD Secure-by-Design — Cybersecurity Project Management Deliverables guide. (11 deliverables after SAD merge)
• PMI / PMBOK Guide — standard PM deliverables. (7 deliverables: PMP, Governance, CRAID, Implementation, Rollback, Test Plan, Req Doc, RTM, UAT, Training, PIR)
• Aligned to CA-PMF; informed by SIMM §19.
Replace this template with the official PPM tool schedule once that tool is in place.

## Schedule
⚠ TEMPLATE — NOT A LIVE PROJECT SCHEDULE ⚠
PM-expected deliverables schedule with Methodology classification (Agile / Waterfall / Both). Combines EDD PM RACI, Secure-by-Design guide, and PMI/PMBOK standards. Phase-parallel scheduling model.
Project Name: | [5 empty] | LWDA Intune Device Migration
Project Manager: | [5 empty] | Delondi Kintaudi
Project Start Date: | [5 empty] | 2026-07-01
Project End Date: | [5 empty] | 7/21/2027 (planned)
Schedule Last Updated: | [5 empty] | 2026-06-17
Project Type: | [5 empty] | Waterfall
Legend: Blue = user input • Source: teal=RACI, gold=Secure-by-Design, violet=PMI • Methodology: orange=Agile, indigo=Waterfall, green=Both • ▶ = phase gate • ║ = parallel sibling
Deliverable ID | Profiler Required? | Schedule Category | Source | Methodology | CA-PMF Phase | Execute Sub-Phase | Baseline Phase | Deliverable / Task | Duration (bus. days) | Planned Start | Planned End | Actual Start | Actual End | Predecessor / Parallelism | Responsible (R) | Status | % Complete | Notes/Assumptions | Comments | Show?
CON-01 | Yes | Governance & Management | RACI | Both | Concept | — | Concept | Obtain Work Intake Confirmation | 1 | 2026-07-01 | 2026-07-01 |  |  | Project Start | Project Sponsor | Not Started | 0% |  |  | Show
INI-01 | Yes | Governance & Management | RACI | Both | Initiate | — | → Close | Develop Project Charter | 10 | 2026-07-02 | 2026-07-15 |  |  | ▶ After Concept | Project Sponsor, IT Sponsor, Project Manager | Not Started | 0% |  |  | Show
INI-02 | Yes | Governance & Management | PMI | Both | Initiate | — | → Close | Develop Project Management Plan(s) | 10 | 2026-07-02 | 2026-07-15 |  |  | ║ Parallel with INI-01 | Project Manager | Not Started | 0% | Defines decision rights and escalation paths. Approved by Steering Committee. |  | Show
INI-03 | Yes | Governance & Management | RACI | Both | Initiate | — | → Close | Develop Stakeholder Register | 5 | 2026-07-02 | 2026-07-08 |  |  | ║ Parallel with INI-01 | Project Sponsor, IT Sponsor, Project Manager | Not Started | 0% |  |  | Show
INI-04 | Yes | Governance & Management | RACI | Both | Initiate | — | Initiate | Review and Revise Engagement Matrix | 5 | 2026-07-02 | 2026-07-08 |  |  | ║ Parallel with INI-01 | Project Sponsor, IT Sponsor, Project Manager | Not Started | 0% |  |  | Show
INI-05 | Yes | Governance & Management | PMI | Both | Initiate | — | → Close | Establish CRAID Log | 5 | 2026-07-02 | 2026-07-08 |  |  | ║ Parallel with INI-01 | Project Manager | Not Started | 0% | Initial setup duration; maintained continuously through Close. |  | Show
INI-06 | Yes | Delivery & Execution | RACI | Both | Initiate | — | → Close | Engage Security Team (refer to CSD Cybersecurity Standards in Notes) | 5 | 2026-07-02 | 2026-07-08 |  |  | ║ Parallel with INI-01 | IT System Owner | Not Started | 0% | CyberSecurity Link |  | Show
INI-07 | Yes | Governance & Management | RACI | Both | Initiate | — | → Close | Develop Enterprise Architecture Engagement Plan | 10 | 2026-07-02 | 2026-07-08 |  |  | ║ Parallel with INI-01 | IT System Owner | Not Started | 0% |  |  | Show
INI-08 | Yes | Governance & Management | RACI | Both | Initiate | — | Initiate | Draft Release Readiness Review (RRR) Checklist | 5 | 2026-07-02 | 2026-07-15 |  |  | ║ Parallel with INI-01 | Project Manager | Not Started | 0% |  |  | Show
PLN-01 | Yes | Governance & Management | PMI | Both | Plan | — | → Close | Consolidate Project Management Plan(s) | 30 | 2026-07-16 | 2026-07-08 |  |  | ▶ After Initiate | Project Manager | Not Started | 0% | Consolidates 8 RACI subsidiary plans (Risk/Issue/Change, Communication, Scope, Requirements, Quality, Organization, Procurement, Cost) per PMBOK guidance. |  | Show
PLN-02 | Yes | Governance & Management | RACI | Both | Plan | — | → Close | Develop Project Schedule | 10 | 2026-07-02 | 2026-08-26 |  |  | ║ Parallel with PLN-01 | Project Manager | Not Started | 0% |  |  | Show
PLN-03 | Yes | Delivery & Execution | RACI | Agile | Plan | — | → Close | Develop Product Vision, Initial Backlog & Sprint Roadmap | 10 | 2026-07-02 | 2026-07-15 |  |  | ║ Parallel with PLN-01 | Project Manager, Scrum Master | Not Started | 0% |  |  | Hide
PLN-04 | Yes | Delivery & Execution | PMI | Waterfall | Plan | — | → Sec Analysis | Gather and Document Requirements | 30 | 2026-07-02 | 2026-07-15 |  |  | ║ Parallel with PLN-01 | Business Analyst | Not Started | 0% | PMBOK standard. Customer/Business accountable; BA executes. Feeds RTM, SAD, test cases. |  | Show
PLN-05 | Yes | Delivery & Execution | PMI | Waterfall | Plan | — | → Test | Develop Test Plan & Test Cases | 10 | 2026-07-02 | 2026-08-12 |  |  | ║ Parallel with PLN-01 | Enterprise Testing Office Lead | Not Started | 0% | PMBOK standard. ETO Lead owned. |  | Show
PLN-06 | Yes | Delivery & Execution | PMI | Both | Plan | — | → Test | Build Requirements Traceability Matrix (RTM) | 20 | 2026-07-02 | 2026-07-15 |  |  | ║ Parallel with PLN-01 | Dev Team Lead, Business Analyst | Not Started | 0% | PMBOK standard. IT-owned; maintained continuously — initial 20 days, ongoing updates. |  | Show
PLN-07 | Yes | Delivery & Execution | RACI | Both | Plan | — | → Design | Develop EA-Level Architecture Models and Diagrams | 15 | 2026-07-02 | 2026-07-29 |  |  | ║ Parallel with PLN-01 | Enterprise Architecture Lead | Not Started | 0% |  |  | Show
PLN-08 | Yes | Governance & Management | PMI | Both | Plan | — | → Implement | Develop Implementation Plan | 15 | 2026-07-02 | 2026-07-22 |  |  | ║ Parallel with PLN-01 | Change and Release Manager | Not Started | 0% | PMBOK transition deliverable. Pairs with Rollback Plan and Go-Live Readiness Plan. |  | Show
PLN-09 | Yes | Governance & Management | PMI | Both | Plan | — | → Implement | Develop Rollback Plan | 10 | 2026-07-02 | 2026-07-22 |  |  | ║ Parallel with PLN-01 | Dev Team Lead, Change and Release Manager | Not Started | 0% | PMBOK risk-management deliverable. Gates go-live approval. |  | Show
PLN-10 | Yes | Delivery & Execution | PMI | Both | Plan | — | → Implement | Develop OCM Training Plan & Materials | 20 | 2026-07-02 | 2026-07-15 |  |  | ║ Parallel with PLN-01 | Organizational Change Manager | Not Started | 0% | PMBOK standard. Org Change Manager drives. Pairs with Transition Plan. |  | Show
PLN-11 | Yes | Governance & Management | RACI | Both | Plan | — | → Implement | Develop Transition Plan | 10 | 2026-07-02 | 2026-07-29 |  |  | ║ Parallel with PLN-01 | Project Manager | Not Started | 0% |  |  | Show
EXE-20 | Yes | Delivery & Execution | RACI | Agile | Execute | Ongoing | → Close | Maintain Product Backlog, Sprint Backlog, Increment & Burndown Artifacts | 160 | 2026-08-27 | 2026-07-15 |  |  | ▶ After Plan | Project Manager, Scrum Master | Not Started | 0% |  |  | Hide
EXE-21 | Yes | Governance & Management | RACI | Both | Execute | Ongoing | → Close | Produce Status Reports | 160 | 2026-07-02 | 2027-04-07 |  |  | ║ Parallel with EXE-19 | Project Manager | Not Started | 0% |  |  | Show
EXE-01 | Yes | Governance & Management | Secure-by-Design | Both | Execute | Sec Analysis | Sec Analysis | Conduct Business Impact Analysis (BIA) | 10 | 2026-08-27 | 2027-02-10 |  |  | ▶ After Plan | Project Manager, EDD Business Owner(s) | Not Started | 0% | ISD/ESG/BCOSS (Andrew Mock) advisory. No duration in guide — placeholder. |  | Show
EXE-02 | Yes | Delivery & Execution | Secure-by-Design | Both | Execute | Sec Analysis | Sec Analysis | Conduct Detailed Privacy Impact Analysis (PIA) | 30 | 2026-07-02 | 2026-09-09 |  |  | ║ Parallel with EXE-01 | IT System Owner | Not Started | 0% | Guide: 30 days. CSD Privacy & Disclosure (Annette Wolfgang) advisory. |  | Show
EXE-03 | Yes | Governance & Management | Secure-by-Design | Both | Execute | Sec Analysis | Sec Analysis | Perform Risk Assessment (RA) | 15 | 2026-07-02 | 2026-08-12 |  |  | ║ Parallel with EXE-01 | CSD Security Lead | Not Started | 0% | Guide: 10–15 days; using upper bound. Legal participation required (no dedicated RACI role). |  | Show
EXE-04 | Yes | Delivery & Execution | Secure-by-Design | Both | Execute | Sec Analysis | Sec Analysis | Draft System Security Plan (SSP) — Sections 1 & 2 | 45 | 2026-07-02 | 2026-07-22 |  |  | ║ Parallel with EXE-01 | IT System Owner | Not Started | 0% | Guide: 30–45 days non-SaaS / 20 days SaaS. Using non-SaaS upper bound. |  | Show
EXE-05 | Yes | Delivery & Execution | RACI | Both | Execute | Design | Design | Facilitate Cloud Review (If Applicable) | 10 | 2027-04-08 | 2026-09-02 |  |  | ▶ After Sec Analysis | Dev Team Lead, Cloud Architecture Lead | Not Started | 0% | If Applicable |  | Show
EXE-06 | Yes | Delivery & Execution | RACI | Both | Execute | Design | Design | Facilitate TARC Preparation | 10 | 2026-07-02 | 2027-04-21 |  |  | ║ Parallel with EXE-05 | Dev Team Lead | Not Started | 0% |  |  | Show
EXE-07 | Yes | Delivery & Execution | Secure-by-Design | Both | Execute | Design | Design | Develop Solution Architecture Document (SAD) | 20 | 2026-07-02 | 2026-07-15 |  |  | ║ Parallel with EXE-05 | Enterprise Architecture Lead, Dev Team Lead | Not Started | 0% | Merged with RACI "Define the Solution Architecture" per PMI consolidation — one architecture deliverable, not two. Performed by EAO. |  | Show
EXE-08 | Yes | Delivery & Execution | Secure-by-Design | Both | Execute | Design | → Implement | Review and Update SSP; Begin Section 3 | 10 | 2026-07-02 | 2026-07-29 |  |  | ║ Parallel with EXE-05 | Project Manager, IT System Owner | Not Started | 0% | Guide notes no additional time beyond meetings — placeholder for control selection workshops. |  | Show
EXE-09 | Yes | Delivery & Execution | Secure-by-Design | Both | Execute | Design | → Implement | Develop Information System Recovery Plan (ISRP) | 15 | 2026-07-02 | 2026-07-15 |  |  | ║ Parallel with EXE-05 | Dev Team Lead | Not Started | 0% | Conditional on BIA outcome (mission-critical = Yes). ISD/ESG guidance. |  | Show
EXE-10 | Yes | Delivery & Execution | Secure-by-Design | Both | Execute | Design | → Implement | Initiate Security Audit Logging (SIEM) | 45 | 2026-07-02 | 2026-07-22 |  |  | ║ Parallel with EXE-05 | Project Manager | Not Started | 0% | Guide: 1–3 months by complexity; midpoint (~45 days). Logged integratioin with Elastic. |  | Show
EXE-11 | Yes | Delivery & Execution | Secure-by-Design | Both | Execute | Design | → Implement | Initiate Vulnerability Assessment (Nessus / Veracode / Prisma Cloud) | 45 | 2026-07-02 | 2026-09-02 |  |  | ║ Parallel with EXE-05 | Project Manager | Not Started | 0% | Guide: 1–3 months by complexity; midpoint (~45 days). |  | Show
EXE-12 | Yes | Delivery & Execution | Secure-by-Design | Both | Execute | Test | Test | Execute System Testing — Vulnerability & Security Scans | 20 | 2027-04-22 | 2026-09-02 |  |  | ▶ After Design | Enterprise Testing Office Lead | Not Started | 0% | Covers CX/UX, performance, and vulnerability testing. Enterprise Testing Office leads. |  | Show
EXE-13 | Yes | Delivery & Execution | Secure-by-Design | Both | Execute | Test | Test | Conduct Application Penetration Testing | 20 | 2026-07-02 | 2027-05-19 |  |  | ║ Parallel with EXE-12 | CSD Security Lead | Not Started | 0% | Guide sizing: Short ≤1 day, Simple ~5 days, Moderate ~10, Complex ~20+ (using Moderate). |  | Show
EXE-14 | Yes | Delivery & Execution | PMI | Both | Execute | Test | Test | Conduct User Acceptance Testing (UAT) | 15 | 2026-07-02 | 2026-07-29 |  |  | ║ Parallel with EXE-12 | Enterprise Testing Office Lead | Not Started | 0% | PMBOK standard. Customer signs off. References Test Plan and RTM. |  | Show
EXE-14A | Yes | Governance & Management | PMI | Both | Execute | Test | Test | *Obtain Cybersecurity Risk Acceptance Form | 15 | 2027-04-22 | 2026-07-22 |  |  | ║ Parallel with EXE-12 | Cyber Security Leads | Not Started | 0% | PMBOK standard. Customer signs off. References Test Plan and RTM. | Done only if the Certification and Accreditation Package is not completed | Show
EXE-15 | Yes | Governance & Management | Secure-by-Design | Both | Execute | Implement | Implement | Obtain Security Certification & Accreditation (C&A) Package | 15 | 2027-05-20 | 2027-05-12 |  |  | ▶ After Test | IT System Owner, CSD Security Lead | Not Started | 0% | Authorizing Officials: CIO/Director/Branch DD/CISO. Re-auth at significant change or ≥3 yrs. Risk Acceptance Form acceptable in lieu of full C&A Package. |  | Show
EXE-16 | Yes | Governance & Management | RACI | Both | Execute | Implement | Implement | Complete LOB Release Readiness Review (RRR) Checklist Prior to RRB | 5 | 2027-04-22 | 2027-06-09 |  |  | ║ Parallel with EXE-15 | Project Manager | Not Started | 0% |  |  | Show
EXE-17 | Yes | Governance & Management | RACI | Both | Execute | Test | → Implement | Schedule and Present RFC for RRB Review | 5 | 2026-07-02 | 2027-04-28 |  |  | ║ Parallel with EXE-12 | Project Manager | Not Started | 0% |  |  | Show
EXE-18 | Yes | Delivery & Execution | RACI | Both | Execute | Test | → Implement | Implement Solution | 3 | 2027-04-22 | 2026-07-08 |  |  | ║ Parallel with EXE-12 | Project Manager | Not Started | 0% |  |  | Show
EXE-19 | Yes | Delivery & Execution | PMI | Both | Execute | Stabilization | Stabilization | Conduct Production Stabilization & Hypercare | 30 | 2027-06-10 | 2027-04-26 |  |  | ▶ After Implement | Project Manager, Dev Team Lead, Transition Support Lead | Not Started | 0% | PMBOK transition deliverable. Standard PM practice; not explicitly called out in EDD RACI or Secure-by-Design guide. Pairs with Transition Plan (PLN-11). |  | Show
CLS-01 | Yes | Governance & Management | RACI | Both | Close | — | Close | Document Lessons Learned | 5 | 2027-06-10 | 2027-07-21 |  |  | ▶ After Execute | Project Manager | Not Started | 0% |  |  | Show
CLS-02 | Yes | Governance & Management | RACI | Both | Close | — | Close | Develop Closeout Report | 10 | 2027-06-10 | 2027-06-16 |  |  | ║ Parallel with CLS-01 | Project Manager | Not Started | 0% |  |  | Show
CLS-03 | [8 empty] | 5 | 2027-06-10 | 2027-06-23 |  |  | ║ Parallel with CLS-01 | Enterprise Architecture Lead | Not Started | 0% |  |  | Hide
CLS-04 | Yes | [7 empty] | 10 | 2027-06-10 | 2027-06-16 |  |  | ║ Parallel with CLS-01 | Project Manager | Not Started | 0% | PMBOK standard. Often pairs with Lessons Learned. |  | Hide
PROJECT SUMMARY | [19 empty] | Hide
Sources: EDD PM RACI Matrix (Mar 4); EDD Secure-by-Design Cybersecurity PM Deliverables guide; PMI/PMBOK Guide. Methodology-tagged for both Waterfall and Agile delivery. Phase-parallel model. Aligned to CA-PMF; informed by SIMM §19. | [19 empty] | Hide
Formulas:
Planned Start = WORKDAY(MAX([Planned End, row above]:[Planned End, row above]),1)
Planned Start = [Planned Start, row above]
Planned End = WORKDAY([Planned Start],[Duration (bus. days)]-1)
Planned End = WORKDAY([Planned Start, row above],[Duration (bus. days), row above]-1)
Note on H14: Project Governance documentation defining Steering Committee charter and membership; decision rights and authority matrix; escalation paths and thresholds; change control authority; reporting cadence; meeting governance; Sponsor/Owner roles. Often paired with the Project Charter.
Note on H17: Project tracking log capturing Changes, Risks, Assumptions, Issues, and Dependencies. Living artifact initiated at project start and maintained continuously through Close. Reviewed at status meetings and steering committee.
Note on H21: Single comprehensive Project Management Plan (PMBOK best practice) integrating all subsidiary management plans: Scope, Requirements, Schedule (mgmt approach), Cost, Quality, Resource/Organization, Communications, Risk/Issue/Change, Procurement, and Stakeholder Engagement. Approved baseline; deviations require change control.
Note on H24: PMBOK requirements deliverable: formal documented business, stakeholder, functional, non-functional, and transition requirements. Owned by customer/business; documented by Business Analyst.
Note on H25: PMBOK quality/test deliverable: test strategy, scope, test environments, schedule, and detailed test cases. Complements the Quality Management Plan and drives downstream System Testing and UAT.
Note on H26: PMBOK traceability deliverable: links each requirement to objectives, design elements, code, test cases, and acceptance criteria. Maintained continuously through System Testing and UAT.
Note on H28: Detailed deployment/rollout plan covering scope, sequence, resources, environments, communication, training delivery, and cutover steps for go-live. Complements Go-Live Readiness Plan (operational readiness) and Transition Plan (handoff to operations).
Note on H29: Documented procedures to revert deployment if go-live fails. Includes trigger criteria, rollback steps, validation checks, communication plan, and recovery time objectives. Required prerequisite for go-live approval.
Note on H30: PMBOK transition deliverable: training strategy, user guides, role-based training materials, and delivery schedule. Required for go-live readiness.
Note on H34: Document business impact if the system is not available. Identify lines of business supported and how they will be impacted. Results inform ISRP and SLA requirements.
Note on H35: Document whether the system will transmit, store, or create PII/FTI. Tied to FIPS 199 information-type identification. (Initiate-phase PIA per RACI is the kick-off; this row is the full delivery.)
Note on H36: Evaluate system design, requirements, and minimum security requirements derived from security categorization to assess effectiveness against potential risks. Facilitated by CSD.
Note on H37: Overview of security requirements and security/privacy controls in place or planned. Sections 1 & 2 cover FIPS 199 categorization and classification.
Note on H40: Architecture/design review and document evaluating planned system design, integration with other systems, and incorporation of shared services and common security controls (authN, DR, IDS, incident reporting). Includes solution architecture definition.
Note on H41: Review and update Sections 1 & 2. Complete Section 3 (NIST SP 800-53 security controls).
Note on H42: Document how to start, recover, and reconstitute system elements: roles/responsibilities, business/tech contacts, alternate site, backup procedures. Required for mission-critical systems only.
Note on H43: Meet with Cybersecurity Operations and Fraud Group to plan SIEM integration. Create Child RFC in Service Manager to initiate SIEM integration.
Note on H44: Meet with Cyber Defense and Response Group (CDRG) to plan integration with Nessus, Veracode, and Prisma Cloud. Create Child RFCs in Service Manager per vulnerability system.
Note on H45: Scan internal- and external-facing systems for vulnerabilities and security deficiencies. Document findings and report to PM/system owner/management for risk acceptance or remediation.
Note on H46: Perform penetration testing against the system. Retest as needed based on findings.
Note on H47: PMBOK validation deliverable: formal customer/business sign-off testing against documented requirements and RTM. Gates go-live.
Note on H48: PMBOK validation deliverable: formal customer/business sign-off testing against documented requirements and RTM. Gates go-live.
Note on H49: Assemble C&A Package: (1) SSP and (2) POA&Ms. ISO certifies controls align with FIPS-199. Authorizing Official (CIO/Director/Branch DD/CISO) renders the accreditation decision.
Note on H53: Post-go-live hypercare period: production monitoring, defect triage and remediation, performance tuning, knowledge transfer to the operations team, and formal transition to steady-state support. Typically 30-60 business days following go-live. Concludes when stabilization exit criteria are met (defect rates within thresholds, system stability KPIs achieved, ops team readiness confirmed).

## Phase Summary
Phase Summary (CA-PMF phases — auto-calculated from Schedule sheet)
Phase | # Deliverables | Total Effort (bus. days) | Phase Start | Phase End | Notes | Working Days | Calendar Days
Concept | 0 | 0 | 0 | 0 | RFC Proposal — gates entry to CA-PMF. | 0 | 1
Initiate | 0 | 0 | 0 | 0 | Charter, Governance, Stakeholder Register, RACI, CRAID Log, security kick-offs. | 0 | 1
Plan | 0 | 0 | 0 | 0 | PMP, Schedule, Requirements Doc, RTM, Test Plan, Training Plan, Implementation/Rollback/Transition Plans, EA Models. | 0 | 1
Execute | 0 | 0 | 0 | 0 | Stages sequence: Sec Analysis → Design → Test → Implement. Ongoing runs throughout. | 0 | 1
Close | 0 | 0 | 0 | 0 | Lessons Learned, Closeout, EA Repo, PIR. | 0 | 1
TOTAL EFFORT | 0 | 0 | 0 | 0 | Effort = sum of deliverable days. Calendar span below = real schedule length.
CALENDAR SPAN (real elapsed) |  | 0 | 0 | 0 | Real project length in business days (parallel-aware). | 0 | 1
By Methodology
Methodology | # Deliverables | Total Effort | First Start | Last End | Notes
Agile | 0 | 0 | 0 | 0 | Agile-only artifacts (Product Backlog, Sprint Backlog). Skip these for Waterfall projects.
Waterfall | 0 | 0 | 0 | 0 | Waterfall-only artifacts (formal Requirements Doc, Test Plan). Skip these for Agile projects (substitutes are in Product Backlog).
Both | 0 | 0 | 0 | 0 | Method-agnostic — included regardless of delivery approach.
By Source
Source | # Deliverables | Total Effort | First Start | Last End | Notes
RACI | 0 | 0 | 0 | 0 | EDD PM RACI Matrix — Mar 4 (25 deliverables after consolidations).
Secure-by-Design | 0 | 0 | 0 | 0 | Cybersecurity PM Deliverables guide (11 deliverables after SAD merge).
PMI | 0 | 0 | 0 | 0 | PMI/PMBOK standards (7 deliverables: PMP, Governance, CRAID, Implementation, Rollback, Test Plan, Req Doc, RTM, UAT, Training, PIR).
Formulas:
Phase Start = MINIFS(Schedule!J12:J57,Schedule!E12:E57,[Phase])
Phase Start = MIN(D4:[Phase Start, row above])
Phase End = MAXIFS(Schedule!K12:K57,Schedule!E12:E57,[Phase])
Phase End = MAX(E4:[Phase End, row above])
Working Days = IF(COUNT([Phase Start]:[Phase End])=2,NETWORKDAYS([Phase Start],[Phase End]),"")
Working Days = NETWORKDAYS([Phase Start],[Phase End])
Total Effort (bus. days) = NETWORKDAYS([Phase Start], [Phase End])

## Contacts
EDD Cybersecurity Support Groups & Contacts
Support Group | Mailbox / Contact | Scope
ITB Enterprise Storage Services Group (ISD / ESG / BCOSS) | edditbenterprisestorageservicesgroup@edd.ca.gov | BIA, ISRP — Andrew Mock guidance.
ITB CSD Privacy Oversight Team | itbcsdprivacyoversightteam@edd.ca.gov | PIA — Annette Wolfgang guidance.
ITB CSD Security Risk and Integrated Risk Management Team | itbcsdsecurityriskandintegratedriskmanagementteam@edd.ca.gov | RA, SSP §1-2 & §3, PenTesting, C&A Package.
ITB CSD Security Policy and Compliance Team | itbcsdsecuritypolicyandcomplianceteam@edd.ca.gov | SSP review/update, control compliance.
ITB TGD Enterprise Architecture Office (EAO) | edditbtgdenterprisearchitectureoffice@edd.ca.gov | SAD review.
Cybersecurity Operations and Fraud Group | (Coordinate via Service Manager — Child RFC) | SIEM integration for security/audit logs.
Cyber Defense and Response Group (CDRG) | cyberdefenseandresponsegroup@edd.ca.gov | Vulnerability tooling: Nessus, Veracode, Prisma Cloud.