## Security Schedule
Project Start (edit to re-base whole schedule) ▶
Project | (from intake) |  | PM | (from intake)
Security review | (from intake) |  | Protected data | (from intake)
Fired by intake | (from intake)
Dates are Excel formulas off B1 — change B1 (or let the Autogenerator stamp the project start) and the whole schedule + Gantt re-base. ⚠ EXTERNAL tasks are anchored provisionally to the project start; wire them to your own project tasks. Bars are conditional formatting (recompute automatically). ◆ = milestone.
Task ID | Category | System / Component | Task Name | Type | Duration (days) | Predecessor IDs | Predecessor (plain English) | Successor IDs | Status | Start | Finish | Notes
1 | CSD - Privacy Policy | Parent rollup | Cyber Security Division Artifacts | Rollup | 81 |  | n/a (rollup) |  |  |  |  | Parent rollup for Privacy Policy + PIA + SSP
2 | CSD - Privacy Policy | All Systems | Privacy Policy Updates | Work | 31 | 11 | After Salesforce/Socure/TRef PIA Complete | 18 |  |  |  | Triggered by PIA completion
3 | CSD - Privacy Policy | All Systems | Update Privacy Notice | Work | 15 | 11 | After Salesforce/Socure/TRef PIA Complete | Ext |  |  |  | Customer-facing notice update. Successor 590 = Execution Complete (external)
4 | CSD - PIA | Parent rollup | Privacy Impact Assessments (PIA) | Rollup | 83 |  | n/a (rollup) |  |  |  |  | PIA group rollup
5 | CSD - PIA | Salesforce/Socure/TRef | Salesforce/Socure/TRef PIA | Rollup | 65 |  | n/a (rollup) |  |  |  |  | Vendor system PIA sub-rollup
6 | CSD - PIA | Salesforce/Socure/TRef | Update and Submit Salesforce/Socure/TRef PIA | Work | 2 | ExtFS-19d | EXTERNAL: starts ~19 days before related design task in main project | 7FS+2d | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Starts PIA cycle
7 | CSD - PIA | Salesforce/Socure/TRef | Review and Approve PIA | Work | 10 | 6FS+2d | After Update and Submit PIA (with 2d lag) | 8 |  |  |  | First CSD review
8 | CSD - PIA | Salesforce/Socure/TRef | OSaaS respond to CSD comments | Work | 36 | 7 | After Review and Approve PIA | 11 |  |  |  | Vendor remediation
9 | CSD - PIA | Salesforce/Socure/TRef | Re-Review PIA due to Scope Change | Work | 13 | Ext | EXTERNAL: scope change trigger | 10 | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Only fires on scope change. Optional in template.
10 | CSD - PIA | Salesforce/Socure/TRef | Review and Approve PIA (post scope change) | Work | 3 | 9 | After Re-Review PIA | 11 |  |  |  | Re-approval. Optional in template.
11 | CSD - PIA | Salesforce/Socure/TRef | Salesforce/Socure/TRef PIA Complete | Milestone | 0 | 8, 10 | After comments resolved AND re-approval | 2, 18, 3 |  |  |  | Unblocks Privacy Policy work
12 | CSD - PIA | Admin Utility | Admin Utility PIA | Rollup | 31 |  | n/a (rollup) |  |  |  |  | Admin Utility PIA sub-rollup
13 | CSD - PIA | Admin Utility | Update and Submit Admin Utility PIA | Work | 4 | ExtFS-6d | EXTERNAL: starts ~6 days before related design task | 14 | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Starts PIA cycle
14 | CSD - PIA | Admin Utility | Review Admin Utility PIA | Work | 11 | 13 | After Update and Submit | 15 |  |  |  | CSD review
15 | CSD - PIA | Admin Utility | Final edits/updates to Admin Utility PIA | Work | 9 | 14 | After Review | 16 |  |  |  | Owner edits
16 | CSD - PIA | Admin Utility | Approve Admin Utility PIA | Work | 7 | 15 | After Final edits | 17 |  |  |  | Final approval
17 | CSD - PIA | Admin Utility | Admin Utility PIA complete | Milestone | 0 | 16 | After Approve | 18 |  |  |  | Milestone
18 | CSD - PIA | All Systems | PIAs complete | Milestone | 0 | Ext, 17, 11, 2 | After all individual PIAs complete + Privacy Policy | 124 | ⚠ Mixed — internal-dated; external leg may push start later |  |  | Group milestone
19 | CSD - SSP | Parent rollup | System Security Plans (SSP) | Rollup | 119 |  | n/a (rollup) |  |  |  |  | SSP group rollup
20 | CSD - SSP | Salesforce/Socure/TRef | Salesforce/Socure/TRef SSP | Rollup | 86 |  | n/a (rollup) |  |  |  |  | Vendor system SSP sub-rollup
21 | CSD - SSP | Salesforce/Socure/TRef | Iterative reviews of Salesforce/Socure/TRef SSP | Work | 81 | ExtFF-10d, ExtSS-15d | EXTERNAL: tied to design finish minus 10d and design start minus 15d | 22 | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Long iterative review cycle with CSD
22 | CSD - SSP | Salesforce/Socure/TRef | Review and Approve SSP | Work | 5 | 21 | After iterative reviews | 23 |  |  |  | Final approval
23 | CSD - SSP | Salesforce/Socure/TRef | Salesforce/Socure/TRef SSP Complete | Milestone | 0 | 22 | After Review and Approve | 106, 37 |  |  |  | Unblocks ASA Testing
24 | CSD - SSP | UIO | UIO SSP | Rollup | 53 |  | n/a (rollup) |  |  |  |  | UIO SSP sub-rollup
25 | CSD - SSP | UIO | Update and Submit UIO SSP | Work | 24 | Ext, Ext, ExtFS+5d | EXTERNAL: after related design and architecture tasks | 37, 26 | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Kickoff
26 | CSD - SSP | UIO | Review and Approve UIO SSP | Work | 29 | 25 | After Update and Submit | 27 |  |  |  | CSD review
27 | CSD - SSP | UIO | UIO SSP complete | Milestone | 0 | 26 | After Review and Approve | 37 |  |  |  | Milestone
28 | CSD - SSP | ICAM | ICAM System Requirement Specification (SSP) | Rollup | 32 |  | n/a (rollup) |  |  |  |  | ICAM SSP sub-rollup
29 | CSD - SSP | ICAM | Update and submit ICAM SSP | Work | 27 | ExtFS+15d | EXTERNAL: 15 days after Dev Finish milestone | 30 | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Kickoff
30 | CSD - SSP | ICAM | Review and Approve ICAM SSP | Work | 5 | 29 | After Update and submit | 31 |  |  |  | CSD review
31 | CSD - SSP | ICAM | ICAM SRS complete | Milestone | 0 | 30 | After Review and Approve | 37 |  |  |  | Milestone
32 | CSD - SSP | Admin Utility | Admin Utility SSP | Rollup | 87 |  | n/a (rollup) |  |  |  |  | Admin Utility SSP sub-rollup
33 | CSD - SSP | Admin Utility | Update and Submit Admin Utility SSP (Initial Draft) | Work | 17 | ExtSS | EXTERNAL: starts with linked dev task | 93SS, 34FS+57d | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Initial draft
34 | CSD - SSP | Admin Utility | Update and Submit SSP Minimum Requirements | Work | 12 | 33FS+57d | 57 days after Initial Draft finish | 98, 35 |  |  |  | Minimum-required SSP path
35 | CSD - SSP | Admin Utility | Approve Admin Utility Minimum required SSP | Work | 1 | 34 | After Minimum Requirements submitted | 36 |  |  |  | Lightweight approval
36 | CSD - SSP | Admin Utility | Admin Utility SSP complete | Milestone | 0 | 35 | After Approve |  |  |  |  | Milestone
37 | CSD - SSP | All Systems | Cyber Security Division Artifacts (PIA & SSP) Complete | Milestone | 0 | 25, 23, 27, 31 | After ALL SSPs complete | 124 |  |  |  | Group milestone (PIA + SSP)
38 | ESG - BIA | Parent rollup | Enterprise Storage Group Artifacts | Rollup | 225 |  | n/a (rollup) |  |  |  |  | ESG parent rollup (BIA + ISRP)
39 | ESG - BIA | Parent rollup | Business Impact Assessments (BIA) | Rollup | 130 |  | n/a (rollup) |  |  |  |  | BIA group rollup
40 | ESG - BIA | Salesforce/Socure/TRef | Salesforce/Socure/TRef BIA | Rollup | 109 |  | n/a (rollup) |  |  |  |  | Sub-rollup
41 | ESG - BIA | Salesforce/Socure/TRef | Update and Submit Salesforce/Socure/TRef BIA | Work | 20 | Ext | EXTERNAL: after myEDD Requirements task | 42 | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Kickoff
42 | ESG - BIA | Salesforce/Socure/TRef | Review and Approve BIA | Work | 89 | 41 | After Update and Submit | 53FS-8d, 43 |  |  |  | ESG review
43 | ESG - BIA | Salesforce/Socure/TRef | Salesforce/Socure/TRef BIA complete | Milestone | 0 | 42 | After Review and Approve | 50 |  |  |  | Unblocks ISRP draft
44 | ESG - BIA | Admin Utility | Admin Utility BIA | Rollup | 48 |  | n/a (rollup) |  |  |  |  | Sub-rollup
45 | ESG - BIA | Admin Utility | Update and Submit BIA | Work | 21 | ExtSS | EXTERNAL: starts with linked dependency | 46 | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Kickoff
46 | ESG - BIA | Admin Utility | Review BIA | Work | 22 | 45 | After Update and Submit | 47 |  |  |  | ESG review
47 | ESG - BIA | Admin Utility | Update BIA | Work | 2 | 46 | After Review | 48 |  |  |  | Owner edits
48 | ESG - BIA | Admin Utility | Approve BIA | Work | 3 | 47 | After Update | 49 |  |  |  | Final approval
49 | ESG - BIA | Admin Utility | Admin Utility BIA complete | Milestone | 0 | 48 | After Approve | 50 |  |  |  | Milestone
50 | ESG - BIA | All Systems | BIA's completed | Milestone | 0 | 43, 49 | After all BIAs complete |  |  |  |  | Group milestone
51 | ESG - ISRP | Parent rollup | Information System Recovery Plan (ISRP) | Rollup | 146 |  | n/a (rollup) |  |  |  |  | ISRP group rollup
52 | ESG - ISRP | Salesforce/Socure/TRef | Salesforce/Socure/TRef ISRP | Rollup | 146 |  | n/a (rollup) |  |  |  |  | Sub-rollup
53 | ESG - ISRP | Salesforce/Socure/TRef | Update and Submit DRAFT ISRP | Work | 2 | 42FS-8d | Starts 8 days before BIA Review finish | 54FS+6d |  |  |  | Draft kickoff
54 | ESG - ISRP | Salesforce/Socure/TRef | Review Draft ISRP | Work | 32 | 53FS+6d | 6 days after Draft submitted | 55 |  |  |  | ESG review
55 | ESG - ISRP | Salesforce/Socure/TRef | Update and Submit FINAL ISRP | Work | 9 | 54 | After Review Draft | 59 |  |  |  | Final submission
56 | ESG - ISRP | Salesforce/Socure/TRef | Re-Review ISRP due to Scope Change | Work | 27 | Ext | EXTERNAL: scope change trigger | 57 | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Only fires on scope change. Optional in template.
57 | ESG - ISRP | Salesforce/Socure/TRef | Update ISRP due to ESG comments | Work | 20 | 56 | After Re-Review | 58 |  |  |  | Remediation
58 | ESG - ISRP | Salesforce/Socure/TRef | Review and Approve FINAL ISRP | Work | 48 | 57 | After Update due to comments | 59 |  |  |  | Final approval
59 | ESG - ISRP | Salesforce/Socure/TRef | Salesforce/Socure/TRef ISRP complete | Milestone | 0 | 58, 55 | After approval | 110, 70 |  |  |  | Unblocks Table Top
60 | ESG - ISRP | Admin Utility | Admin Utility ISRP | Rollup | 143 |  | n/a (rollup) |  |  |  |  | Sub-rollup
61 | ESG - ISRP | Admin Utility | Update and Submit Admin Utility ISRP | Work | 43 | Ext | EXTERNAL: after linked design task | 62 | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Kickoff
62 | ESG - ISRP | Admin Utility | Update Admin Utility ISRP per ESG feedback | Work | 42 | 61 | After Update and Submit | 64FS+3d |  |  |  | Remediation
63 | ESG - ISRP | Admin Utility | Submit After Action Plan | Work | 7 | 112 | After UIO Table Top Walkthrough | 65 |  |  |  | Post-walkthrough
64 | ESG - ISRP | Admin Utility | Review and Approve Admin Utility ISRP | Work | 61 | 62FS+3d | 3 days after Update finish | 65 |  |  |  | ESG review
65 | ESG - ISRP | Admin Utility | Admin Utility ISRP Complete | Milestone | 0 | 64, 63 | After Approve and After Action Plan | 70, 111FS-5d |  |  |  | Milestone
66 | ESG - ISRP | UIO | UIO ISRP | Rollup | 72 |  | n/a (rollup) |  |  |  |  | Sub-rollup
67 | ESG - ISRP | UIO | Update and Submit UIO ISRP | Work | 22 | Ext | EXTERNAL: after linked design task | 68, 112FS-1d | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Kickoff
68 | ESG - ISRP | UIO | Review and Approve UIO ISRP | Work | 50 | 67 | After Update and Submit | 69 |  |  |  | ESG review
69 | ESG - ISRP | UIO | UIO ISRP Complete | Milestone | 0 | 68 | After Review and Approve | 70 |  |  |  | Milestone
70 | ESG - ISRP | All Systems | ISRP's Complete | Milestone | 0 | 65, 59, 69 | After all ISRPs complete | 124 |  |  |  | Group milestone
71 | ITB - Technical Design | Parent rollup | ITB Artifacts | Rollup | 188 |  | n/a (rollup) |  |  |  |  | ITB parent rollup
72 | ITB - Technical Design | Parent rollup | Technical Design | Rollup | 159 |  | n/a (rollup) |  |  |  |  | TD group rollup
73 | ITB - Technical Design | All Systems | Develop and Submit Technical Design Document (Nav Screens) | Work | 10 | Ext | EXTERNAL: after Requirement Gathering Complete | 74 | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Kickoff
74 | ITB - Technical Design | All Systems | Review Technical Design | Work | 41 | 73 | After Develop and Submit | 76FS-5d, 75 |  |  |  | ITB review
75 | ITB - Technical Design | Socure | Socure Navigational Screens added to Technical Design | Work | 13 | 74 | After Review | 77 |  |  |  | Socure-specific addition
76 | ITB - Technical Design | TRef | TRef Navigational Screens added to Technical Design | Work | 26 | 74FS-5d | 5 days before Review finish | 77FS+62d |  |  |  | TRef-specific addition
77 | ITB - Technical Design | All Systems | Approve myEDD Navigation Flow | Work | 25 | 75, 76FS+62d | After both nav additions | 78 |  |  |  | Final approval
78 | ITB - Technical Design | All Systems | Technical Design Complete | Milestone | 0 | 77 | After Approve | 124, 81FS-4d, 89FS-3d |  |  |  | Unblocks SAD work
79 | ITB - SAD | Parent rollup | System Architectural Design (SAD) | Rollup | 124 |  | n/a (rollup) |  |  |  |  | SAD group rollup
80 | ITB - SAD | OSaaS | OSaaS SAD/ICD(OCP)/ICD(SCP ID+) | Rollup | 53 |  | n/a (rollup) |  |  |  |  | Sub-rollup
81 | ITB - SAD | OSaaS | Update and Submit SAD | Work | 4 | Ext, Ext, Ext, 78FS-4d | EXTERNAL design tasks + 4d before TD Complete | 82 | ⚠ Mixed — internal-dated; external leg may push start later |  |  | Kickoff
82 | ITB - SAD | OSaaS | Review and Approve SAD | Work | 49 | 81 | After Update and Submit | 83 |  |  |  | ITB review
83 | ITB - SAD | OSaaS | OSaaS SAD/ICD(OCP)/ICD(SCP ID+) complete | Milestone | 0 | 82 | After Review and Approve | 96 |  |  |  | Milestone
84 | ITB - SAD | UIO | UIO SAD | Rollup | 63 |  | n/a (rollup) |  |  |  |  | Sub-rollup
85 | ITB - SAD | UIO | Update and Submit UIO SAD | Work | 24 | Ext, ExtFS+5d | EXTERNAL: after related design tasks | 86 | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Kickoff
86 | ITB - SAD | UIO | Review and Approve UIO SAD | Work | 39 | 85 | After Update and Submit | 87 |  |  |  | ITB review
87 | ITB - SAD | UIO | UIO SAD complete | Milestone | 0 | 86 | After Review and Approve | 96 |  |  |  | Milestone
88 | ITB - SAD | ICAM | ICAM SAD | Rollup | 32 |  | n/a (rollup) |  |  |  |  | Sub-rollup
89 | ITB - SAD | ICAM | Update and Submit ICAM SAD | Work | 22 | 78FS-3d | 3 days before TD Complete | 90 |  |  |  | Kickoff
90 | ITB - SAD | ICAM | Review and Approve ICAM SAD | Work | 10 | 89 | After Update and Submit | 91 |  |  |  | ITB review
91 | ITB - SAD | ICAM | ICAM SAD complete | Milestone | 0 | 90 | After Review and Approve | 96 |  |  |  | Milestone
92 | ITB - SAD | Admin Utility | Admin Utility SAD | Rollup | 20 |  | n/a (rollup) |  |  |  |  | Sub-rollup
93 | ITB - SAD | Admin Utility | Update and Submit Admin Utility SAD | Work | 17 | Ext, 33SS | EXTERNAL design task; starts with SSP Initial Draft | 94 | ⚠ Mixed — internal-dated; external leg may push start later |  |  | Kickoff
94 | ITB - SAD | Admin Utility | Review and Approve Admin Utility SAD | Work | 3 | 93 | After Update and Submit | 95 |  |  |  | ITB review
95 | ITB - SAD | Admin Utility | Admin Utility SAD complete | Milestone | 0 | 94 | After Review and Approve | 96 |  |  |  | Milestone
96 | ITB - SAD | All Systems | Security Architectural Designs (SAD) complete | Milestone | 0 | 95, 83, 87, 91 | After all SADs complete | 124 |  |  |  | Group milestone
97 | C&A (ATO) | Parent rollup | Certification and Accreditation (C&A) | Rollup | 24 |  | n/a (rollup) |  |  |  |  | C&A parent rollup
98 | C&A (ATO) | All Systems | Create SSP Certification and Accreditation Package | Work | 12 | 108FS-8d, 34 | After ASA Testing Complete -8d AND Admin Util SSP Min Reqs | 99 |  |  |  | Package creation
99 | C&A (ATO) | All Systems | Route C&A Package for Approval | Work | 10 | 98 | After Create Package | 100 |  |  |  | Routing
100 | C&A (ATO) | All Systems | Receive C&A Approval | Work | 2 | 99 | After Route | 101 |  |  |  | Approval
101 | C&A (ATO) | All Systems | C&A complete (Approval to Operate (ATO) is signed) | Milestone | 0 | 100 | After Receive Approval | 124 |  |  |  | ATO - gates go-live
102 | Security Testing | Parent rollup | Application Security Assessment (ASA) / Penetration Testing (Pen) | Rollup | 35 |  | n/a (rollup) |  |  |  |  | ASA parent rollup
103 | Security Testing | All Systems | Define ASA testing data | Work | 1 | ExtFS+3d | EXTERNAL: 3 days after linked test task | 104FS+10d, 105 | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Kickoff
104 | Security Testing | All Systems | Data Preparation | Work | 10 | 103FS+10d | 10 days after Define ASA testing data | 106 |  |  |  | Test data prep
105 | Security Testing | All Systems | Hold Rules of Engagement Meeting | Work | 1 | 103 | After Define ASA testing data | 106 |  |  |  | Engagement meeting
106 | Security Testing | All Systems | Conduct ASA Testing (iterative) | Work | 5 | 104, 23, ExtFS-1d, 105 | After Data Prep AND Salesforce SSP Complete AND EXTERNAL test task AND Rules of Engagement | 107 | ⚠ Mixed — internal-dated; external leg may push start later |  |  | Pen testing
107 | Security Testing | All Systems | ASA remediation | Work | 7 | 106 | After Conduct ASA Testing | 108 |  |  |  | Fix findings
108 | Security Testing | All Systems | ASA Testing Complete | Milestone | 0 | 107 | After remediation | Ext, 98FS-8d |  |  |  | Unblocks C&A Package
109 | Table Top Walkthrough | Parent rollup | Table Top Walkthrough | Rollup | 9 |  | n/a (rollup) |  |  |  |  | Tabletop drill parent rollup
110 | Table Top Walkthrough | myEDD | myEDD Execute Table Top Walkthrough | Work | 1 | 59 | After Salesforce/Socure/TRef ISRP Complete | 113 |  |  |  | Drill execution
111 | Table Top Walkthrough | Admin Utility | Admin Util Execute Table Top Walkthrough | Work | 1 | 65FS-5d | 5 days before Admin Util ISRP Complete | 113 |  |  |  | Drill execution
112 | Table Top Walkthrough | UIO | UIO Execute Table Top Walkthrough | Work | 1 | 67FS-1d | 1 day before UIO ISRP Update finish | 113, 63 |  |  |  | Drill execution
113 | Table Top Walkthrough | All Systems | Table Top Walkthroughs complete | Milestone | 0 | 110, 111, 112 | After all walkthroughs complete | Ext |  |  |  | Group milestone
114 | CSD Elastic (Logging) | Parent rollup | Cyber Security Division (CSD) Elastic Development | Rollup | 169 |  | n/a (rollup) |  |  |  |  | Elastic logging parent rollup
115 | CSD Elastic (Logging) | All Systems | Submit Elastic Log Ingestion and Dashboard Specifications | Work | 1 | ExtFS-3d | EXTERNAL: 3 days before Review Requirements Complete | 116FS+30d | ⚠ EXTERNAL — provisional from project start; wire to your project task |  |  | Spec submission
116 | CSD Elastic (Logging) | All Systems | Submit Elastic Intake Form | Work | 4 | 115FS+30d | 30 days after Specs | 117FS+43d |  |  |  | Intake form
117 | CSD Elastic (Logging) | All Systems | Engagement & Initial Discovery | Work | 15 | 116FS+43d | 43 days after Intake Form | 118, 119 |  |  |  | Discovery
118 | CSD Elastic (Logging) | Salesforce | Salesforce Log Integration | Work | 37 | 117 | After Engagement | 120 |  |  |  | Log integration
119 | CSD Elastic (Logging) | Gateway | Gateway Log Integration | Work | 37 | 117 | After Engagement | 120 |  |  |  | Log integration
120 | CSD Elastic (Logging) | Socure | Verification of Socure Log Ingestion | Work | 2 | 118, 119 | After all log integrations | 121, 122 |  |  |  | Verification
121 | CSD Elastic (Logging) | All Systems | Verify data against source | Work | 2 | 120 | After Verification | 122FS+3d |  |  |  | Data verification
122 | CSD Elastic (Logging) | All Systems | Dashboard buildout | Work | 32 | 120, 121FS+3d | After Verification | 123 |  |  |  | Dashboard work
123 | CSD Elastic (Logging) | All Systems | CSD Elastic Development complete | Milestone | 0 | 122 | After Dashboard buildout |  |  |  |  | Group milestone
124 | Final Rollup | All Systems | Artifact Delivery Complete | Milestone | 0 | 70, 37, 18, 96, 78, 101 | After ALL artifact milestones (ISRP, PIA+SSP group, PIAs, SAD, TD, C&A) | Ext |  |  |  | FINAL ARTIFACT GATE

## Abbreviations
Abbreviations | Expansion | Category
SSP | System Security Plan. | Security and Compliance Artifacts
PIA | Privacy Impact Assessment. | Security and Compliance Artifacts
PTA | Privacy Threshold (Assessment). | Security and Compliance Artifacts
BIA | Business Impact Assessment. | Security and Compliance Artifacts
ISRP | Information System Recovery Plan. | Security and Compliance Artifacts
TRP | Technology Recovery Plan. | Security and Compliance Artifacts
POAMs | Plan of Action and Milestones. | Security and Compliance Artifacts
SAD | System Architectural Design/Security Architectural Designs | Security and Compliance Artifacts
ASA | Application Security Assessment. | Security and Compliance Artifacts
Pen | Penetration Testing. | Security and Compliance Artifacts
C&A | Certification and Accreditation. | Security and Compliance Artifacts
ATO | Approval to Operate. | Security and Compliance Artifacts
SRS |  | Security and Compliance Artifacts
SLA |  | Security and Compliance Artifacts
RFC |  | Security and Compliance Artifacts
CSD | Cyber Security Division. | Organizations, Divisions, Groups
PMO | Project Management Office. | Organizations, Divisions, Groups
ESPMO | Enterprise Strategies and Project Management Office. | Organizations, Divisions, Groups
EPMO | Enterprise Services & Project Management Office. | Organizations, Divisions, Groups
PDG | Project Delivery Group | Organizations, Divisions, Groups
CRMG | Change and Release Management Group. | Organizations, Divisions, Groups
IT | Information Technology. | Organizations, Divisions, Groups
EDD | Employment Development Department | Organizations, Divisions, Groups
ESG |  | Organizations, Divisions, Groups
ITB |  | Organizations, Divisions, Groups
ISD |  | Organizations, Divisions, Groups
EAO |  | Organizations, Divisions, Groups
EOA |  | Organizations, Divisions, Groups
EWG |  | Organizations, Divisions, Groups
PMOG |  | Organizations, Divisions, Groups
TG |  | Organizations, Divisions, Groups
CDT |  | Organizations, Divisions, Groups
ELT |  | Organizations, Divisions, Groups
MIC |  | Organizations, Divisions, Groups
PRO |  | Organizations, Divisions, Groups
LOB |  | Organizations, Divisions, Groups
IDP |  | Systems, Products, Initiatives
ICAM |  | Systems, Products, Initiatives
ICMS |  | Systems, Products, Initiatives
UIO |  | Systems, Products, Initiatives
UIB |  | Systems, Products, Initiatives
UI |  | Systems, Products, Initiatives
UX |  | Systems, Products, Initiatives
CX |  | Systems, Products, Initiatives
LMS |  | Systems, Products, Initiatives
ETO |  | Systems, Products, Initiatives
PMF |  | Systems, Products, Initiatives
myEDD |  | Systems, Products, Initiatives
EDDNext |  | Systems, Products, Initiatives
EA |  | Project and Technical Terms
CMD |  | Project and Technical Terms
ISA |  | Project and Technical Terms
MVP |  | Project and Technical Terms
POC |  | Project and Technical Terms
OCM |  | Project and Technical Terms
ICD |  | Project and Technical Terms
OCP |  | Project and Technical Terms
SCP |  | Project and Technical Terms
UAT |  | Project and Technical Terms
QA |  | Project and Technical Terms
API |  | Project and Technical Terms
SSN |  | Project and Technical Terms
AI |  | Project and Technical Terms
OSaaS |  | Project and Technical Terms
TRef |  | Project and Technical Terms

## How to Use
Security Artifact Task Template
Workbook contents
Security Tasks Template | Full task list (1 through 124) grouped by category. Each row has Task ID, Category, System/Component, Task Name, Type, Duration, Predecessors (with internal IDs remapped), Predecessor plain English, Successors, and Notes. AutoFilter on. Freeze panes at column E.
Reading the Predecessor / Successor columns
Numeric IDs (e.g. 11, 23, 37) | These reference OTHER tasks in this template. Look up that Task ID in Sheet 1 to see the linked task.
"Ext" entries | EXTERNAL dependency. This is linked to a task that lives outside this artifact template (e.g. a design task, a scope-change trigger, a Requirements milestone). The Predecessor plain English column tells you what kind of external task to wire it to in YOUR project schedule.
FS / SS / FF suffixes with day offsets | Standard Microsoft Project link types. FS = Finish-to-Start, SS = Start-to-Start, FF = Finish-to-Finish. "FS-8d" means the predecessor must finish 8 days BEFORE this task can start. "SS+5d" means starts 5 days after predecessor starts.
Categories
CSD - Privacy Policy | Privacy Policy Updates + Update Privacy Notice. Triggered after PIA Complete.
CSD - PIA | Privacy Impact Assessment per system. Pattern: Update/Submit > Review > (Remediate / Re-review) > Approve > Complete.
CSD - SSP | System Security Plan per system. Pattern: Update/Submit Initial Draft > Iterative reviews > Review and Approve > Complete.
ESG - BIA | Business Impact Assessment per system. Owned by Enterprise Storage Group. Pattern: Update/Submit > Review > Update > Approve > Complete.
ESG - ISRP | Information System Recovery Plan per system. Pattern: Draft > Review Draft > Final > (Re-review if scope change) > Approve Final > Complete.
ITB - Technical Design | Pre-requisite to SAD. Pattern: Develop and Submit > Review > Approve > Complete.
ITB - SAD | System Architectural Design per system. Pattern: Update/Submit > Review and Approve > Complete.
C&A (ATO) | Certification and Accreditation. Final gate. Creates SSP C&A Package, routes for approval, receives ATO sign-off.
Security Testing | Application Security Assessment / Pen Testing. Runs after SSPs complete and before C&A package.
Table Top Walkthrough | Operational readiness drill per system. Runs after ISRP work.
CSD Elastic (Logging) | Log ingestion + dashboard for monitoring. Runs in parallel with main artifact work.
Final Rollup | Artifact Delivery Complete. The single gate that all artifact streams must clear before project Execution Complete.
How to use for a new project
Step 1 | Identify which systems your project touches (Here we have assumed 4 systems: Salesforce/Socure/TRef, UIO, ICAM, Admin Utility). Each system needs its own PIA, SSP, BIA, ISRP, SAD chain.
Step 2 | Filter Sheet 1 by Category. Copy the rows for each category into your project schedule, duplicating per system.
Step 3 | Re-base the dates. Durations are the source of truth; start dates depend on your project plan.
Step 4 | Wire up the predecessor links. Internal IDs (numeric) point to other rows in this template. "Ext" entries need to be wired to YOUR project tasks (design, requirements, scope-change triggers).
Step 5 | Confirm assignments. Douglas Leone confirmed PMs do not complete these tasks. Assign to a CSD resource or System Owner.
Step 6 | Validate against the Dependency Map sheet to ensure all streams feed into the Final Rollup milestone.
System Owner ownership | SSP and PIA sit under the System Owner in the RACI, not the Project Manager. PM coordinates and schedules; System Owner is accountable for content.
Confidentiality | Completed SSPs and PIAs are confidential. Do not share verbatim content across projects. Use task structure only.
Re-review for scope change | Both PIA and ISRP have Re-Review tasks marked EXTERNAL because they are triggered by a scope-change event on the main project. Include these as conditional tasks in your template.